## Restoration Daily Report
start | end | test | project_site | site_type | site_name | site_name/nursery_kirui | site_name/transplanting_kirui_shangani | site_name/transplanting_kirui_corner | site_name/transplanting_kirui_exp | site_name/nursery_kigombe | site_name/transplanting_kigombe_taa | site_name/transplanting_kigome_makome | site_name/nursery_msuka | site_name/transplanting_msuka_panga_punge | restoration_team | restoration_team/shabani | restoration_team/burhani | restoration_team/phares | restoration_team/adam | restoration_team/yusuf | restoration_team/omary | restoration_team/nusra | restoration_team/gerad | restoration_team/abbakar | restoration_team/jean | restoration_team/pagu | restoration_team/jumbe | restoration_team/mwindadi | restoration_team/athumani | restoration_team/ben | restoration_team/mbarouk_hamad | restoration_team/rashid_said | restoration_team/hemeduni_abdalla | number_of_other_participants | Date | Start_time | End_time | tide | Site_depth | water_temperature | water_clarity | select_activity | select_activity/fragmentation | select_activity/transplantation | select_activity/monitoring | select_activity/cleaning_and_maintaining | number_of_fragments_installed_on_tables | number_of_tables_installed | total_number_of_fragments_transplanted | total_number_of_structures_transplanted | number_of_tables_monitored | number_of_tables_cleaned | total_tables_in_nursery_to_date | total_fragments_in_nursery_to_date | total_reef_starts_deployed_to_date | total_fragments_on_reef_stars_to_date | total_fence_wires_deployed_to_date | total_fragments_on_fence_wires_to_date | total_fragments_on_clips_to_date | total_fragments_transplanted_to_date | Remarks_comments_observations | Add_photos | Add_video | _id | _uuid | _submission_time | _validation_status | _notes | _status | _submitted_by | __version__ | _tags | meta/rootUuid | _index
2026-07-06T19:52:43.300+03:00 | 2026-07-10T19:02:18.908+03:00 | no | moa | nursery | [10 empty] | phares adam yusuf omary nusra hemeduni_abdalla | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2026-07-06 | 09:30:00.000+03:00 | 01:00:00.000+03:00 | falling | 9 | 27 | 6 | cleaning_and_maintaining | 0 | 0 | 0 | 1 | [5 empty] | 6 |  |  | 305 |  | 6 | [6 empty] | 803631047 | 723c6a83-f234-4435-960a-bb9dc3480fa6 | 2026-07-06T17:14:31 |  |  | submitted_via_web | wcs_tanzania | v55AV6dH7kjPAvdHKtEVVG |  | uuid:eb086f57-a704-4efc-a15a-f61cc9de615b | 1
2026-07-08T15:09:58.366+03:00 | 2026-07-08T16:21:10.990+03:00 | no | moa | nursery | [10 empty] | phares adam yusuf omary nusra hemeduni_abdalla | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2026-07-08 | 11:30:00.000+03:00 | 14:30:00.000+03:00 | falling | 8 | 26 | 7 | fragmentation | 1 | 0 | 0 | 0 | [8 empty] | 305 |  | 6 | [6 empty] | 805337414 | e92153d7-1cf6-44a3-9e8e-3a20d9d3c999 | 2026-07-08T13:21:52 |  |  | submitted_via_web | wcs_tanzania | vCkHvrKwcRQ5DbaMoYkkd6 |  | uuid:81e06e4e-2c8d-423a-9066-8acdd02fff7c | 2
2026-07-09T17:38:54.031+03:00 | 2026-07-24T11:35:08.099+03:00 | no | moa | nursery | nursery_kirui | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phares adam yusuf omary nusra hemeduni_abdalla | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2026-07-09 | 10:00:00.000+03:00 | 13:30:00.000+03:00 | falling | 9 | 26 | 7 | fragmentation | 1 | 0 | 0 | 0 | 280 | 2 |  |  |  |  | 48 | 10688 | 305 | 3965 | 6 | 3500 | 0 | 7465 | none | P5060091-17_48_57.JPG |  | 806506452 | 9e0a8ccb-06c7-4cce-9aac-936442432ca7 | 2026-07-09T14:52:46 |  |  | submitted_via_web | wcs_tanzania | vqNFtU5FCbU6qmGgWH2f6a |  | uuid:22730a20-cf8d-4fa7-a94a-4eb023d8da89 | 3
2026-07-10T17:42:10.959+03:00 | 2026-07-24T11:41:49.869+03:00 | no | moa | nursery | nursery_kirui | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phares adam yusuf omary nusra hemeduni_abdalla | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2026-07-10 | 10:00:00.000+03:00 | 16:00:00.000+03:00 | falling | 9 | 27 | 7 | fragmentation | 1 | 0 | 0 | 0 | 784 | 4 |  |  |  |  | 48 | 11472 | 305 | 3965 | 6 | 3500 | 0 | 7465 | none | P5080108-17_50_58.JPG |  | 807657551 | af9162e3-dade-46d1-a114-8ccfa734203a | 2026-07-10T14:52:06 |  |  | submitted_via_web | wcs_tanzania | vqNFtU5FCbU6qmGgWH2f6a |  | uuid:65f95ea3-ee4c-44bc-bed9-156549361a9d | 4
2026-07-13T12:19:41.314+03:00 | 2026-07-13T12:51:54.010+03:00 | no | kigombe | transplanting | [10 empty] | abbakar jumbe mwindadi athumani | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 5 | 2026-07-06 | 12:45:00.000+03:00 | 15:45:00.000+03:00 | rising | 8 | 22 | 9 | transplantation | 0 | 1 | 0 | 0 | [8 empty] | 208 |  | 0 | [6 empty] | 809373757 | b8ce9a44-60c5-4922-af43-156e29bfba7e | 2026-07-13T09:52:22 |  |  | submitted_via_web | wcs_tanzania | vqNFtU5FCbU6qmGgWH2f6a |  | uuid:aa8f08e0-9321-4d16-a158-baaa6c5a7454 | 5
2026-07-13T12:51:54.042+03:00 | 2026-07-13T13:03:23.618+03:00 | no | kigombe | [11 empty] | abbakar jumbe mwindadi athumani | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2026-07-08 | 08:30:00.000+03:00 | 13:00:00.000+03:00 | rising | 8 | 23 | 6 | cleaning_and_maintaining | 0 | 0 | 0 | 1 | [5 empty] | 8 |  |  | 208 |  | 0 | [6 empty] | 809385709 | 43a37268-be3c-440c-9f9a-511ed27f39eb | 2026-07-13T10:03:26 |  |  | submitted_via_web | wcs_tanzania | vqNFtU5FCbU6qmGgWH2f6a |  | uuid:43a37268-be3c-440c-9f9a-511ed27f39eb | 6
2026-07-13T13:03:23.647+03:00 | 2026-07-13T13:07:15.915+03:00 | no | kigombe | transplanting | [10 empty] | abbakar jumbe mwindadi athumani | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2026-07-09 | 10:15:00.000+03:00 | 15:00:00.000+03:00 | rising | 7 | 23 | 8 | cleaning_and_maintaining | 0 | 0 | 0 | 1 | [5 empty] | 9 |  |  | 208 |  | 0 | [6 empty] | 809390319 | 38ee1eb4-06df-4080-84c4-ec201dda3e8f | 2026-07-13T10:07:16 |  |  | submitted_via_web | wcs_tanzania | vqNFtU5FCbU6qmGgWH2f6a |  | uuid:8e1528e9-df26-4dc4-a323-f28fa2409672 | 7
2026-07-13T13:07:15.954+03:00 | 2026-07-13T13:11:05.929+03:00 | no | kigombe | transplanting | [10 empty] | abbakar jumbe mwindadi athumani | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2026-07-10 | 09:30:00.000+03:00 | 14:30:00.000+03:00 | rising | 8 | 24 | 5 | cleaning_and_maintaining | 0 | 0 | 0 | 1 | [5 empty] | 6 |  |  | 208 |  | 0 | [6 empty] | 809394701 | 4261bdc6-98b5-48d7-b8d5-5857319ce592 | 2026-07-13T10:11:06 |  |  | submitted_via_web | wcs_tanzania | vqNFtU5FCbU6qmGgWH2f6a |  | uuid:8e4ea9ed-2706-4f45-abd8-83647806c8dd | 8
2026-07-13T17:04:08.167+03:00 | 2026-07-13T17:11:24.043+03:00 | no | moa | transplanting | [10 empty] | adam yusuf omary nusra pagu hemeduni_abdalla | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2026-07-13 | 09:00:00.000+03:00 | 15:00:00.000+03:00 | falling | 10 | 26 | 7 | fragmentation | 1 | 0 | 0 | 0 | [8 empty] | 305 |  | 10 |  |  |  |  | P5100134-17_11_20.JPG |  | 809892839 | d5b7962a-390d-46b4-99f0-38c87b2fe178 | 2026-07-13T17:11:32 |  |  | submitted_via_web | wcs_tanzania | vqNFtU5FCbU6qmGgWH2f6a |  | uuid:90c08df0-f81e-4a47-a016-6ff87b2ba120 | 9
2026-07-08T08:48:20.511+03:00 | 2026-07-15T11:28:42.624+03:00 | no | msuka | nursery | [10 empty] | burhani mbarouk_hamad rashid_said | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2026-07-06 | 09:00:00.000+03:00 | 15:00:00.000+03:00 | rising | 8 | 26 | 5 | cleaning_and_maintaining | 0 | 0 | 0 | 1 | [5 empty] | 15 |  |  | 240 |  | 0 | [6 empty] | 810629008 | 1f798809-4836-4b16-b5fa-4c1951596259 | 2026-07-14T11:08:57 |  |  | submitted_via_web | wcs_tanzania | vCkHvrKwcRQ5DbaMoYkkd6 |  | uuid:a93e9bf5-9324-4d75-90bd-b552ac7eec9e | 10
2026-07-08T09:13:17.260+03:00 | 2026-07-15T11:32:42.958+03:00 | no | msuka | transplanting | [10 empty] | shabani burhani | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-08 | 08:00:00.000+03:00 | 16:00:00.000+03:00 | rising | 9 | 26 | 6 | transplantation | 0 | 1 | 0 | 0 | [8 empty] | 250 |  | 0 | [6 empty] | 810679559 | b17cca2a-40a2-458c-8168-1168eb65d3d6 | 2026-07-14T11:55:04 |  |  | submitted_via_web | wcs_tanzania | vqNFtU5FCbU6qmGgWH2f6a |  | uuid:80fe4fd5-afa2-4238-8caa-700b4d003f9a | 11
2026-07-14T17:13:43.394+03:00 | 2026-07-14T17:37:53.021+03:00 | no | moa | transplanting | [10 empty] | adam yusuf omary nusra hemeduni_abdalla | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2026-07-14 | 09:00:00.000+03:00 | 14:30:00.000+03:00 | falling | 11 | 26 | 11 | fragmentation transplantation | 1 | 1 | 0 | 0 | [8 empty] | 305 |  | 10 | [6 empty] | 810853924 | 62a31b1e-5c19-4c9d-a71e-7da2277c8bca | 2026-07-14T14:38:26 |  |  | submitted_via_web | wcs_tanzania | vqNFtU5FCbU6qmGgWH2f6a |  | uuid:e9cbce53-1311-411d-91db-4bca321a400b | 12
2026-07-14T14:54:56.221+03:00 | 2026-07-14T20:05:51.188+03:00 | no | msuka | nursery | [10 empty] | shabani burhani | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-01 | 07:30:00.000+03:00 | 21:30:00.000+03:00 | high | 11 | 27 | 7 | cleaning_and_maintaining | 0 | 0 | 0 | 1 | [5 empty] | 10 |  |  | 240 |  | 0 | [6 empty] | 810990369 | 8beb7b51-d9f6-4508-9e0b-8742c165e847 | 2026-07-14T16:36:02 |  |  | submitted_via_web | wcs_tanzania | vqNFtU5FCbU6qmGgWH2f6a |  | uuid:a8de2c7a-a5b6-4775-adf7-7cc7daf8806c | 13
2026-07-14T19:35:54.460+03:00 | 2026-07-14T19:58:06.396+03:00 | no | msuka | nursery | [10 empty] | shabani burhani | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-02 | 07:45:00.000+03:00 | 15:45:00.000+03:00 | low | 8 | 26 | 6 | cleaning_and_maintaining | 0 | 0 | 0 | 1 | [5 empty] | 12 |  |  | 240 |  | 0 | [6 empty] | 810996729 | 19b8da63-beb4-4ec6-8ea6-102b34c50c5a | 2026-07-14T16:41:23 |  |  | submitted_via_web | wcs_tanzania | vqNFtU5FCbU6qmGgWH2f6a |  | uuid:bd4495ac-30cf-42b1-a333-5807562ae40c | 14
2026-07-14T19:41:15.120+03:00 | 2026-07-14T19:57:29.565+03:00 | no | msuka | nursery | [10 empty] | shabani burhani | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-03 | 08:00:00.000+03:00 | 16:00:00.000+03:00 | low | 7 | 26 | 6 | cleaning_and_maintaining | 0 | 0 | 0 | 1 | [5 empty] | 15 |  |  | 240 |  | 0 | [6 empty] | 811005610 | fb3041f3-6fa7-403c-a862-22d3861dac67 | 2026-07-14T16:49:50 |  |  | submitted_via_web | wcs_tanzania | vqNFtU5FCbU6qmGgWH2f6a |  | uuid:f191c12a-4e8f-43e7-b2b8-3bed3721c320 | 15
2026-07-14T19:49:41.832+03:00 | 2026-07-15T11:37:36.899+03:00 | no | msuka | transplanting | [10 empty] | shabani burhani | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-09 | 07:45:00.000+03:00 | 15:40:00.000+03:00 | high | 13 | 25 | 6 | transplantation | 0 | 1 | 0 | 0 | [8 empty] | 260 |  | 0 | [6 empty] | 811519969 | d7568da5-ea67-4ae8-b58e-aa0075bebbee | 2026-07-15T08:37:59 |  |  | submitted_via_web | wcs_tanzania | vU7fWA2ufbhKeAhbVCM2aR |  | uuid:abb5d1ab-e051-4862-bd5e-40c06fe89d7d | 16
2026-07-15T11:37:36.924+03:00 | 2026-07-15T11:44:11.364+03:00 | no | msuka | nursery | [10 empty] | shabani burhani | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-10 | 08:30:00.000+03:00 | 16:20:00.000+03:00 | rising | 8 | 26 | 6 | fragmentation | 1 | 0 | 0 | 0 | [8 empty] | 260 |  | 0 | [6 empty] | 811526938 | cccb3ec5-8544-43dd-ab4c-a00abd0723fd | 2026-07-15T08:44:12 |  |  | submitted_via_web | wcs_tanzania | vU7fWA2ufbhKeAhbVCM2aR |  | uuid:8fc7e36b-bd41-47eb-a1fc-d21cc96e474c | 17
2026-07-15T11:44:11.389+03:00 | 2026-07-15T12:12:39.531+03:00 | no | msuka | nursery | [10 empty] | shabani burhani | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-13 | 08:05:00.000+03:00 | 16:00:00.000+03:00 | low | 8 | 26 | 7 | transplantation | 0 | 1 | 0 | 0 | [8 empty] | 270 |  | 0 | [6 empty] | 811555782 | 7a8c538d-8487-4174-8cbd-40cf98e65d40 | 2026-07-15T09:12:42 |  |  | submitted_via_web | wcs_tanzania | vU7fWA2ufbhKeAhbVCM2aR |  | uuid:85f261f1-5740-4686-8d28-8a4174c0bc9f | 18
2026-07-15T12:12:39.554+03:00 | 2026-07-15T12:21:05.243+03:00 | no | msuka | transplanting | [10 empty] | shabani burhani | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-14 | 08:30:00.000+03:00 | 16:30:00.000+03:00 | rising | 9 | 26 | 6 | transplantation | 0 | 1 | 0 | 0 | [8 empty] | 280 |  | 0 | [6 empty] | 811564995 | 3130ddf8-123b-4465-ac63-8a84e75d470c | 2026-07-15T09:21:05 |  |  | submitted_via_web | wcs_tanzania | vU7fWA2ufbhKeAhbVCM2aR |  | uuid:ecf523be-a8b3-4072-a8c3-e5429ac201c1 | 19
2026-07-15T12:21:05.267+03:00 | 2026-07-15T21:49:03.117+03:00 | no | msuka | transplanting | [10 empty] | shabani burhani | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-15 | 08:45:00.000+03:00 | 21:45:00.000+03:00 | rising | 12 | 27 | 6 | transplantation | 0 | 1 | 0 | 0 | [8 empty] | 290 |  | 0 | [6 empty] | 812141286 | 7707989a-8447-4288-8cff-4373d20974c9 | 2026-07-15T18:49:33 |  |  | submitted_via_web | wcs_tanzania | vU7fWA2ufbhKeAhbVCM2aR |  | uuid:87fb6d03-8c1f-4128-9ba3-803e061d2c05 | 20
2026-07-16T19:42:07.399+03:00 | 2026-07-16T19:47:33.877+03:00 | no | moa | transplanting | [10 empty] | phares adam yusuf omary nusra pagu hemeduni_abdalla | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2026-07-16 | 09:00:00.000+03:00 | 13:00:00.000+03:00 | falling | 10 | 26 | 8 | transplantation | 0 | 1 | 0 | 0 | [8 empty] | 305 |  | 10 |  |  |  |  | P5130349-19_47_28.JPG |  | 813127665 | a62913b5-b69f-48c1-b0a1-ee5d470e9507 | 2026-07-16T16:47:44 |  |  | submitted_via_web | wcs_tanzania | vU7fWA2ufbhKeAhbVCM2aR |  | uuid:a0a95e17-922f-4b43-ac4a-e59c3322e00e | 21
2026-07-15T21:49:03.164+03:00 | 2026-07-16T20:21:20.027+03:00 | no | msuka | transplanting | [10 empty] | shabani burhani | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-16 | 20:30:00.000+03:00 | 15:30:00.000+03:00 | rising | 12 | 25 | 7 | transplantation | 0 | 1 | 0 | 0 | [8 empty] | 240 |  | 0 | [6 empty] | 813166498 | 5f4e9038-cf5c-48cc-99b7-05ecb6035a5d | 2026-07-16T17:21:36 |  |  | submitted_via_web | wcs_tanzania | vU7fWA2ufbhKeAhbVCM2aR |  | uuid:fb98aa79-7388-40d5-9359-40215b1ac838 | 22
2026-07-16T20:21:20.078+03:00 | 2026-07-17T21:09:24.502+03:00 | no | msuka | nursery | [10 empty] | shabani burhani | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-17 | 07:15:00.000+03:00 | 12:05:00.000+03:00 | falling | 10 | 26 | 7 | cleaning_and_maintaining | 0 | 0 | 0 | 1 | [5 empty] | 12 |  |  | 300 |  | 0 | [6 empty] | 814289828 | 847968b4-2a3f-4a4f-8c15-96ab4aff16f8 | 2026-07-17T18:09:47 |  |  | submitted_via_web | wcs_tanzania | vU7fWA2ufbhKeAhbVCM2aR |  | uuid:201f8009-f81e-4c91-99b0-590c647f9d9f | 23
2026-07-18T20:18:04.070+03:00 | 2026-07-18T20:26:14.978+03:00 | no | moa | transplanting | [10 empty] | phares adam yusuf omary nusra pagu hemeduni_abdalla | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2026-07-17 | 09:00:00.000+03:00 | 14:00:00.000+03:00 | falling | 11 | 26 | 10 | transplantation | 0 | 1 | 0 | 0 | [8 empty] | 305 |  | 10 |  |  |  |  | P5130345-20_23_50.JPG |  | 814961031 | 79ad2513-3ff4-42ce-a7ab-6c8b67c7505f | 2026-07-18T17:24:17 |  |  | submitted_via_web | wcs_tanzania | vU7fWA2ufbhKeAhbVCM2aR |  | uuid:3e7d8c3a-19f6-4f93-9070-2e3c40090d32 | 24
2026-07-20T19:44:03.980+03:00 | 2026-07-20T19:50:30.873+03:00 | no | moa | transplanting | [10 empty] | phares adam yusuf omary nusra pagu hemeduni_abdalla | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2026-07-20 | 09:00:00.000+03:00 | 13:30:00.000+03:00 | falling | 11 | 26 | 9 | transplantation | 0 | 1 | 0 | 0 | [8 empty] | 305 |  | 10 |  |  |  |  | 1000173732-19_44_9.jpg |  | 816321425 | 469225f0-c36c-4f7e-9b48-d9f4eed5b875 | 2026-07-20T16:50:34 |  |  | submitted_via_web | wcs_tanzania | vT2zLGSZAAa7Qfb9mt87HE |  | uuid:469225f0-c36c-4f7e-9b48-d9f4eed5b875 | 25
2026-07-21T16:42:38.693+03:00 | 2026-07-21T18:23:10.437+03:00 | no | moa | transplanting | [10 empty] | phares adam yusuf omary nusra pagu hemeduni_abdalla | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2026-07-21 | 08:30:00.000+03:00 | 13:30:00.000+03:00 | falling | 12 | 26 | 6 | transplantation | 0 | 1 | 0 | 0 |  |  | 288 |  |  |  | 48 | 11248 | 305 | 3965 | 10 | 11004 | 0 | 14969 | None | 1000173712-16_47_50.jpg |  | 817249040 | e9fc0099-dd8d-4533-9a34-96547957265e | 2026-07-21T13:48:29 |  |  | submitted_via_web | wcs_tanzania | vPVmMyaak3ALKykyZ8cyac |  | uuid:9e78919e-8a05-4fbd-b50e-c9af8a9c380b | 26
2026-07-17T21:09:24.554+03:00 | 2026-07-21T19:11:37.123+03:00 | no | msuka | transplanting | [10 empty] | shabani burhani | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-20 | 07:15:00.000+03:00 | 14:45:00.000+03:00 | falling | 12 | 26 | 7 | transplantation | 0 | 1 | 0 | 0 |  |  | 430 |  |  |  | 64 | 14723 | 310 | 4030 | 0 | 0 | 11400 | 15430 | Transplantation is going on |  |  | 817440309 | e92bafdd-b75f-4e5a-a27e-c37177dd6192 | 2026-07-21T16:12:03 |  |  | submitted_via_web | wcs_tanzania | vPVmMyaak3ALKykyZ8cyac |  | uuid:e92bafdd-b75f-4e5a-a27e-c37177dd6192 | 27
2026-07-21T19:11:37.177+03:00 | 2026-07-21T19:17:22.024+03:00 | no | msuka | transplanting | [10 empty] | shabani burhani | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-21 | 08:15:00.000+03:00 | 21:15:00.000+03:00 | falling | 12 | 26 | 6 | transplantation | 0 | 1 | 0 | 0 |  |  | 430 |  |  |  | 64 | 14423 | 320 | 4160 | 0 | 0 | 11700 | 15860 | team need epoxy and wire for fragmentation and maintanance |  |  | 817447071 | 6166a4b7-d7ce-40a9-8cf9-8054f2ff6a78 | 2026-07-21T16:17:27 |  |  | submitted_via_web | wcs_tanzania | vPVmMyaak3ALKykyZ8cyac |  | uuid:6166a4b7-d7ce-40a9-8cf9-8054f2ff6a78 | 28
2026-07-22T12:45:27.355+03:00 | 2026-07-22T12:54:08.239+03:00 | no | kigombe | nursery | [10 empty] | abbakar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-14 | 09:00:00.000+03:00 | 13:00:00.000+03:00 | falling | 6 | 25 | 10 | cleaning_and_maintaining | 0 | 0 | 0 | 1 | [5 empty] | 0 | 85 | 12432 | 208 | 2704 | 0 | 0 | 24013 | 26717 | Big great barracuda was seen in the nursery |  |  | 818140391 | b48d335b-049a-4cbe-98f8-0629b08f3518 | 2026-07-22T09:57:45 |  |  | submitted_via_web | wcs_tanzania | vPVmMyaak3ALKykyZ8cyac |  | uuid:b48d335b-049a-4cbe-98f8-0629b08f3518 | 29
2026-07-22T12:54:40.549+03:00 | 2026-07-22T13:04:48.272+03:00 | no | kigombe | nursery | [10 empty] | athumani | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 2026-07-15 | 08:45:00.000+03:00 | 13:30:00.000+03:00 | falling | 7 | 24 | 8 | cleaning_and_maintaining monitoring | 0 | 0 | 1 | 1 |  |  |  |  | 4 | 4 | 85 | 12432 | 208 | 2704 | 0 | 0 | 24013 | 26717 |  |  |  | 818150627 | 110051b7-fcd7-4b2b-9910-74a79a4af33c | 2026-07-22T10:05:12 |  |  | submitted_via_web | wcs_tanzania | vPVmMyaak3ALKykyZ8cyac |  | uuid:110051b7-fcd7-4b2b-9910-74a79a4af33c | 30
2026-07-22T13:06:34.923+03:00 | 2026-07-22T13:15:43.075+03:00 | no | kigombe | nursery | [10 empty] | jumbe | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-16 | 09:00:00.000+03:00 | 02:00:00.000+03:00 | falling | 7 | 20 | 9 | cleaning_and_maintaining | 0 | 0 | 0 | 1 | [5 empty] | 4 | 85 | 12432 | 208 | 2704 | 0 | 0 | 24013 | 26717 |  |  |  | 818165883 | 0bc19b72-73b4-444f-89c6-5d1cca6fc7e9 | 2026-07-22T10:16:25 |  |  | submitted_via_web | wcs_tanzania | vPVmMyaak3ALKykyZ8cyac |  | uuid:0bc19b72-73b4-444f-89c6-5d1cca6fc7e9 | 31
2026-07-22T13:10:49.872+03:00 | 2026-07-22T13:24:21.470+03:00 | no | kigombe | nursery | [10 empty] | mwindadi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 2026-07-17 | 08:40:00.000+03:00 | 12:45:00.000+03:00 | falling | 7 | 22 | 6 | fragmentation | 1 | 0 | 0 | 0 | 12432 | 0 |  |  |  |  | 85 | 12432 | 208 | 2704 | 0 | 0 | 24013 | 26717 |  |  |  | 818177839 | 6946094b-4fd4-40c1-83e5-33e603ae0db0 | 2026-07-22T10:26:41 |  |  | submitted_via_web | wcs_tanzania | vPVmMyaak3ALKykyZ8cyac |  | uuid:6946094b-4fd4-40c1-83e5-33e603ae0db0 | 32
2026-07-22T13:27:26.397+03:00 | 2026-07-22T13:34:56.113+03:00 | no | kigombe | nursery | [10 empty] | abbakar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2026-07-20 | 09:00:00.000+03:00 | 13:00:00.000+03:00 | high | 8 | 20 | 9 | fragmentation | 1 | 0 | 0 | 0 | 336 | 0 |  |  |  |  | 85 | 12768 | 208 | 2704 | 0 | 0 | 24013 | 26717 |  |  |  | 818187740 | 40b6211a-0a18-4867-be8e-aff9d07c3b64 | 2026-07-22T10:35:05 |  |  | submitted_via_web | wcs_tanzania | vPVmMyaak3ALKykyZ8cyac |  | uuid:40b6211a-0a18-4867-be8e-aff9d07c3b64 | 33
2026-07-22T13:17:52.071+03:00 | 2026-07-22T13:50:04.603+03:00 | no | kigombe | nursery | [10 empty] | athumani | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 2026-07-21 | 09:00:00.000+03:00 | 02:40:00.000+03:00 | high | 9 | 25 | 8 | fragmentation | 1 | 0 | 0 | 0 | 252 | 0 |  |  |  |  | 85 | 13024 | 208 | 2704 | 0 | 0 | 24313 | 27017 |  |  |  | 818212929 | 862c4378-0e8d-4111-a074-018e848d358e | 2026-07-22T10:56:30 |  |  | submitted_via_web | wcs_tanzania | vPVmMyaak3ALKykyZ8cyac |  | uuid:862c4378-0e8d-4111-a074-018e848d358e | 34
2026-07-22T13:48:45.920+03:00 | 2026-07-22T13:56:52.497+03:00 | no | kigombe | nursery | [10 empty] | mwindadi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2026-07-22 | 20:40:00.000+03:00 | 13:50:00.000+03:00 | high | 9 | 25 | 10 | fragmentation | 1 | 0 | 0 | 0 | 336 | 0 |  |  |  |  | 85 | 13360 | 208 | 2704 | 0 | 0 | 24313 | 27017 |  |  |  | 818215934 | 725b45b8-dfb8-449d-943a-bc5807f65f00 | 2026-07-22T10:59:08 |  |  | submitted_via_web | wcs_tanzania | vPVmMyaak3ALKykyZ8cyac |  | uuid:725b45b8-dfb8-449d-943a-bc5807f65f00 | 35
2026-07-22T19:54:24.820+03:00 | 2026-07-22T19:58:05.836+03:00 | no | moa | transplanting | [10 empty] | phares adam yusuf omary nusra pagu hemeduni_abdalla | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2026-07-22 | 08:30:00.000+03:00 | 14:00:00.000+03:00 | falling | 11 | 26 | 7 | transplantation | 0 | 1 | 0 | 0 |  |  | 408 |  |  |  | 48 | 11248 | 305 | 3965 | 10 | 11412 | 0 | 15377 | Non | P5190428-19_58_2.JPG |  | 818750938 | 3de5c4e8-ec1e-4e51-a7dd-c0b880a8cee6 | 2026-07-22T16:58:08 |  |  | submitted_via_web | wcs_tanzania | vPVmMyaak3ALKykyZ8cyac |  | uuid:3de5c4e8-ec1e-4e51-a7dd-c0b880a8cee6 | 36
2026-07-24T11:47:17.748+03:00 | 2026-07-24T11:53:00.097+03:00 | no | moa | nursery | nursery_kirui | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phares adam yusuf omary nusra hemeduni_abdalla | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2026-07-11 | 08:30:00.000+03:00 | 14:00:00.000+03:00 | falling | 9 | 26 | 8 | fragmentation | 1 | 0 | 0 | 0 | 196 | 2 |  |  |  |  | 28 | 11668 | 305 | 3965 | 6 | 3500 | 0 | 7465 | none |  |  | 820345947 | 40ecfdba-51d1-45b8-8df7-9ff56121ddbc | 2026-07-24T08:53:17 |  |  | submitted_via_web | wcs_tanzania | vUqA9CvcWY6YRPkqP3iBRf |  | uuid:40ecfdba-51d1-45b8-8df7-9ff56121ddbc | 37
2026-07-24T12:05:05.216+03:00 | 2026-07-24T12:29:25.392+03:00 | no | moa | transplanting | transplanting_kirui_shangani | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phares adam yusuf omary nusra hemeduni_abdalla | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2026-07-23 | 08:30:00.000+03:00 | 14:00:00.000+03:00 | falling | 11 | 26 | 6 | transplantation | 0 | 1 | 0 | 0 |  |  | 508 | 1 |  |  | 48 | 11248 | 305 | 3965 | 10 | 5706 | 0 | 9671 | none | P5170375-12_9_35.JPG |  | 820360178 | 1bd10172-df83-4c8d-b75c-0034ddc16785 | 2026-07-24T09:09:45 |  |  | submitted_via_web | wcs_tanzania | vUqA9CvcWY6YRPkqP3iBRf |  | uuid:13e22352-8bea-42ac-ad5b-383c608e4124 | 38
2026-07-24T12:22:34.441+03:00 | 2026-07-24T12:30:56.974+03:00 | no | moa | transplanting | transplanting_kirui_shangani | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phares adam yusuf omary nusra hemeduni_abdalla | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2026-07-24 | 09:00:00.000+03:00 | 12:30:00.000+03:00 | rising | 11 | 26 | 8 | transplantation | 0 | 1 | 0 | 0 |  |  | 168 | 1 |  |  | 48 | 11248 | 305 | 3965 | 10 | 5874 | 0 | 9839 | none | P5110207-12_26_26.JPG |  | 820374744 | 41d3cefd-d034-4e2d-80c5-3ea041c1778f | 2026-07-24T09:26:36 |  |  | submitted_via_web | wcs_tanzania | vUqA9CvcWY6YRPkqP3iBRf |  | uuid:6f1f1cca-6fb8-4b2c-897f-5efd9f675c62 | 39

## fragments_transplanted_loop
number_of_fragments_transplanted | type_of_support | other_support | _index | _parent_table_name | _parent_index | _submission__id | _submission__uuid | _submission__submission_time | _submission__validation_status | _submission__notes | _submission__status | _submission__submitted_by | _submission___version__ | _submission__tags | _submission_meta/rootUuid
508 | fence_wire |  | 1 | Restoration Daily Report | 38 | 820360178 | 1bd10172-df83-4c8d-b75c-0034ddc16785 | 2026-07-24T09:09:45 |  |  | submitted_via_web | wcs_tanzania | vUqA9CvcWY6YRPkqP3iBRf |  | uuid:13e22352-8bea-42ac-ad5b-383c608e4124
168 | fence_wire |  | 2 | Restoration Daily Report | 39 | 820374744 | 41d3cefd-d034-4e2d-80c5-3ea041c1778f | 2026-07-24T09:26:36 |  |  | submitted_via_web | wcs_tanzania | vUqA9CvcWY6YRPkqP3iBRf |  | uuid:6f1f1cca-6fb8-4b2c-897f-5efd9f675c62

## support_structures_installed...
number_of_support_structures_installed | type_of_support_structure_installed | other_structure | _index | _parent_table_name | _parent_index | _submission__id | _submission__uuid | _submission__submission_time | _submission__validation_status | _submission__notes | _submission__status | _submission__submitted_by | _submission___version__ | _submission__tags | _submission_meta/rootUuid
1 | fence_wire |  | 1 | Restoration Daily Report | 38 | 820360178 | 1bd10172-df83-4c8d-b75c-0034ddc16785 | 2026-07-24T09:09:45 |  |  | submitted_via_web | wcs_tanzania | vUqA9CvcWY6YRPkqP3iBRf |  | uuid:13e22352-8bea-42ac-ad5b-383c608e4124
1 | fence_wire |  | 2 | Restoration Daily Report | 39 | 820374744 | 41d3cefd-d034-4e2d-80c5-3ea041c1778f | 2026-07-24T09:26:36 |  |  | submitted_via_web | wcs_tanzania | vUqA9CvcWY6YRPkqP3iBRf |  | uuid:6f1f1cca-6fb8-4b2c-897f-5efd9f675c62